Internship Preliminary Project Plan

| Intern Name | TBD - intern to enter full legal/preferred name |
| --- | --- |
| Intern Email Contact | TBD - intern email |
| Intern Phone Number | TBD - intern phone |
| Date | June 16, 2026 |
| Project Name | Europa Dirty-Ice Radar Confidence Modeling and Validation |
| Mentor Name | TBD - confirm with mentor |
| Mentor Email | TBD - mentor email |
| Mentor Phone Number | TBD - mentor phone |
| Co-Mentor | TBD / N/A if not assigned |
| Co- Mentor Email | TBD / N/A |
| Co-Mentor Phone Number | TBD / N/A |

Intern Schedule

Full-time interns are expected to work 40 hours/week on average. Part-time interns are expected to work 15-20 hours a week on average depending on the initial agreement listed in the offer letter. Students are required to set their active core working hours with their mentor. Please list the agreed upon working schedule below (e.g., 9 am-5 pm Monday-Friday).

| Active Core Hours | Proposed: 9:00 AM-5:00 PM Monday-Friday, with core mentor overlap 10:00 AM-3:00 PM Pacific Time. Final schedule to be confirmed with mentor. |
| --- | --- |

Project Objectives:

Please list the top three project objectives and provide a short description for each, such as the general tasks required, resources needed, the anticipated outcome (e.g., technical outcomes, educational benefits, etc.), and the objective deadline/timeline.

Objective 1:

| Objective | Define and validate the project baseline for Europa dirty-ice radar interpretation. |
| --- | --- |
| Tasks | Review the REASON HF/VHF radar context and the current workbook, Python scripts, CSV outputs, and generated charts. Document model scope, assumptions, units, and caveats so the work is framed as a sensitivity simulation rather than a mission-grade processor. Identify the main interpretation risk: when dirty or heterogeneous ice, internal layers, or surface clutter can make a bright echo look like the ocean boundary. |
| Resources Required | Local Python simulation files, Excel workbook outputs, generated CSV summaries, REASON instrument references, NASA Europa Clipper instrument context, and mentor feedback. |
| Anticipated Outcome | A clear research question, traceable source map, baseline assumptions, and validation checklist for the simulation and final deliverables. |
| Anticipated Challenges | Keeping claims appropriately limited, reconciling workbook and Python assumptions, and avoiding over-interpretation where lab dielectric data or full-wave modeling is not available. |
| Deadline/Timeline | Weeks 1-2: complete source inventory, baseline review, assumptions table, and initial mentor check-in. |
| Collaboration Groups | Mentor and any available radar/science reviewers for scope, terminology, and assumption checks. |

Objective 2:

| Objective | Build and refine a reproducible dirty-ice radar confidence model. |
| --- | --- |
| Tasks | Compare clean ice, salt-reference, briny/mushy lens, stacked dirty layers, complex dirty ice, and clutter stress cases across HF 9 MHz and VHF 60 MHz bands. Calculate interpretation metrics such as ocean confidence score, ambiguous-or-false percentage, attenuation risk, false-layer risk, surface-clutter risk, and not-interpretable percentage. Create case studies showing confident ocean returns, false-layer confusion, rough-surface clutter, attenuation-hidden ocean returns, and shallow/internal-feature-only cases. |
| Resources Required | Python, pandas, generated v2/v3 simulation outputs, confidence-summary CSVs, uncertainty-range tables, charting tools, and workbook/dashboard files. |
| Anticipated Outcome | A reproducible confidence-layer simulation that helps distinguish likely ocean candidates from internal-layer or clutter-driven false positives under stated assumptions. |
| Anticipated Challenges | Model simplifications, lack of real Europa REASON data, VHF deep-detection limits, sensitivity to attenuation assumptions, and separating shallow reflectors from ocean-depth calls. |
| Deadline/Timeline | Weeks 3-6: run/refine scenarios, review metrics, update confidence outputs, and complete a mid-project technical review. |
| Collaboration Groups | Mentor for science review; possible data/modeling peers for code review, sanity checks, and interpretation feedback. |

Objective 3:

| Objective | Package the research into a final dashboard, technical explanation, and presentation-ready summary. |
| --- | --- |
| Tasks | Prepare concise charts and tables showing scenario comparisons, confidence-score ranges, risk components, and representative false-ocean case studies. Write a methods/results narrative that explains what the model can and cannot claim, including the distinction between sensitivity simulation and mission data processing. Deliver a final workbook/dashboard, short technical memo or report, and presentation/demo for mentor review. |
| Resources Required | Final CSV outputs, Excel workbook/dashboard, generated charts, technical notes, project plan, and mentor-approved framing language. |
| Anticipated Outcome | A polished final project package that communicates the research question, model method, key findings, uncertainty, and next-step recommendations. |
| Anticipated Challenges | Condensing technical material for a mixed audience, preserving traceability from claims to files, and presenting uncertainty without weakening the value of the project. |
| Deadline/Timeline | Weeks 7-final week: finalize visuals and narrative, complete mentor revisions, rehearse presentation, and submit final deliverables by the internship end date. |
| Collaboration Groups | Mentor/co-mentor for final review; presentation audience or project stakeholders for feedback on clarity and usefulness. |

Roles and Responsibilities

Defined roles and responsibilities provide clarity, alignment, and expectations for everyone working on this project. Defining these roles can make a positive impact on how the work is done and enables effective communication throughout the completion of the project. Please provide a brief description (use bullet points if preferred) for each role, cooperatively with your mentor.

| Intern Role | Research and modeling intern focused on Europa radar interpretation risk and confidence scoring. |
| --- | --- |
| Intern Responsibilities | Maintain the local code/data workspace and keep outputs traceable to scripts, assumptions, and source files. Run and validate simulation scenarios; summarize results with appropriate units, caveats, and uncertainty language. Meet agreed core hours, provide regular progress updates, ask for review when assumptions are uncertain, and prepare final deliverables. |
| Mentor Role | Set project priorities and success criteria; confirm the research question, scope, and timeline. Review assumptions, terminology, caveats, and final deliverables; help connect the work to mission/science context. |
| Co-Mentor Role | If assigned, provide technical or science review of the radar/modeling approach, help sanity-check outputs, and give feedback on the final presentation. If no co-mentor is assigned, mark N/A. |